## S2
Task | Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 02. Medical Record Management | 2.02 | Upload & Store Medical Documents | Implement secure document upload API (HIPAA encryption) | Y | 3/26/2025 | 2025-03-27 | 100% | Vedang
2 | 02. Medical Record Management | 2.02 | Upload & Store Medical Documents | Test file upload with invalid formats/sizes | Y | 3/26/2025 | 2025-03-28 | 100% | Vedang
3 | 02. Medical Record Management | 2.03 | Prescription Refill Requests | Test upload with invalid formats | Y | 2025-03-27 | 2025-03-29 | 40% | Sashank
4 | 02. Medical Record Management | 2.03 | Prescription Refill Requests | Performance test with concurrent users | Y | 2025-03-27 | 2025-04-01 | 30% | Vedang
5 | 02. Medical Record Management | 2.03 | Prescription Refill Requests | Build doctor approval workflow | Y | 2025-03-28 | 2025-04-02 | 30% | Vedang
6 | 02. Medical Record Management | 2.03 | Prescription Refill Requests | Validate doctor-only approval access | Y | 2025-03-29 | 2025-04-03 | 20% | Malavika
7 | 02. Medical Record Management | 2.03 | Prescription Refill Requests | Send patient notifications for refill status | Y | 2025-03-30 | 2025-04-04 | 10% | Malavika
8 | 03.Billing & Finance | 3.01 | Online Payment Processing | Integrate payment gateway | N | 2025-04-02 | 2025-05-04 | 0% | Malavika
9 | 03.Billing & Finance | 3.01 | Online Payment Processing | Implement payment retry logic | N | 2025-04-03 | 2025-05-04 | 0% | Malavika
10 | 03.Billing & Finance | 3.01 | Online Payment Processing | Log payment gateway errors | N | 2025-05-04 | 2025-06-04 | 0% | Malavika
11 | 03.Billing & Finance | 3.01 | Online Payment Processing | Test failed transactions (invalid card/offline) | N | 2025-04-06 | 2025-07-04 | 0% | Sashank
12 | 03.Billing & Finance | 3.02 | Create Invoice | Design auto-tax invoice template | N | 2025-04-07 | 2025-08-04 | 0% | Sashank
13 | 03.Billing & Finance | 3.02 | Create Invoice | Track invoice status (Draft→Pending→Paid) | N | 2025-04-08 | 2025-09-04 | 0% | Vedang
14 | 03.Billing & Finance | 3.02 | Create Invoice | Validate invoice totals against services | N | 2025-04-09 | 2025-10-04 | 0% | Vedang
15 | 03.Billing & Finance | 3.03 | Update Invoice | Implement concurrency control for edits | N | 2025-04-10 | 2025-11-04 | 0% | Vedang
16 | 03.Billing & Finance | 3.03 | Update Invoice | Validate editable fields | N | 2025-04-11 | 2025-12-04 | 0% | Sashank
17 | 03.Billing & Finance | 3.03 | Update Invoice | Log all invoice changes (user, timestamp, old/new values) | Y | 2025-04-12 | 13/4/2025 | 0% | Sashank
18 | 03.Billing & Finance | 3.03 | Update Invoice | Implement approval workflow for major changes (>10% amount) | N | 2025-04-13 | 14/4/2025 | 0% | Malavika
19 | 03.Billing & Finance | 3.03 | Update Invoice | Test error handling for invalid edits (e.g., locked invoices) | Y | 2025-04-13 | 14/4/2025 | 0% | Malavika

## S3
Task | Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 03.Billing & Finance | 3.04 | Delete Invoice | Design database schema to support soft delete flag | Y | 2025-04-16 | 2025-04-17 | 100% | Vedang
=A1+1 | 03.Billing & Finance | 3.04 | Delete Invoice | Implement backend logic to mark invoice as deleted | Y | 2025-04-16 | 2025-04-17 | 100% | Vedang
=A1+2 | 03.Billing & Finance | 3.04 | Delete Invoice | Update UI to show 'Archived' status for deleted invoices | Y | 2025-04-17 | 2025-04-18 | 100% | Vedang
=A1+3 | 03.Billing & Finance | 3.04 | Delete Invoice | Write unit tests for archive/unarchive flows | N | 2025-04-17 | 2025-04-18 | 100% | Vedang
4 | 03.Billing & Finance | 3.05 | Approve Invoice | Add threshold logic for invoice approval | Y | 2025-04-18 | 2025-04-19 | 100% | Malavika
5 | 03.Billing & Finance | 3.05 | Approve Invoice | Create UI for approving/rejecting invoices | Y | 2025-04-18 | 2025-04-19 | 100% | Sashank
6 | 03.Billing & Finance | 3.05 | Approve Invoice | Conduct role-based approval scenario testing | Y | 2025-04-19 | 2025-04-20 | 100% | Sashank
7 | 03.Billing & Finance | 3.05 | Approve Invoice | Write Test Cases: Role-based approval/override scenarios | N | 2025-04-19 | 2025-04-20 | 100% | Sashank
8 | 03.Billing & Finance | 3.06 | Create Insurance Claim | Auto-fill patient demographics from medical records | Y | 2025-04-20 | 2025-04-21 | 100% | Vedang
9 | 03.Billing & Finance | 3.06 | Create Insurance Claim | Identify required medical fields for claim | Y | 2025-04-20 | 2025-04-21 | 100% | Vedang
10 | 03.Billing & Finance | 3.06 | Create Insurance Claim | Test if medical codes are correct | N | 2025-04-21 | 2025-04-22 | 100% | Malavika
11 | 03.Billing & Finance | 3.06 | Create Insurance Claim | Write test cases for auto-fill functionality | N | 2025-04-21 | 2025-04-22 | 100% | Malavika
12 | 03.Billing & Finance | 3.07 | Update Insurance Claim | Design draft-saving functionality | Y | 2025-04-22 | 2025-04-23 | 100% | Malavika
13 | 03.Billing & Finance | 3.07 | Update Insurance Claim | Add validation for editable fields | Y | 2025-04-22 | 2025-04-23 | 100% | Sashank
14 | 03.Billing & Finance | 3.07 | Update Insurance Claim | Write Test Cases: Draft save and field validation | N | 2025-04-23 | 2025-04-24 | 100% | Sashank
15 | 03.Billing & Finance | 3.07 | Update Insurance Claim | Test error handling for concurrent edits | N | 2025-04-23 | 2025-04-24 | 100% | Malavika
16 | 03.Billing & Finance | 3.08 | Submit Insurance Claim | Identify insurance provider API endpoints | Y | 2025-04-24 | 2025-04-25 | 100% | Malavika
17 | 03.Billing & Finance | 3.08 | Submit Insurance Claim | Develop backend integration for submission | Y | 2025-04-24 | 2025-04-25 | 100% | Vedang
18 | 03.Billing & Finance | 3.08 | Submit Insurance Claim | Secure API keys and tokens | N | 2025-04-25 | 2025-04-26 | 100% | Vedang
19 | 03.Billing & Finance | 3.08 | Submit Insurance Claim | Perform integration testing | N | 2025-04-25 | 2025-04-26 | 100% | Vedang
20 | 04.Doctor and Clinical Management | 4.02 | Secure Doctor Patient Communication | Implement end-to-end encryption for chat module | Y | 2025-04-26 | 2025-04-27 | 100% | Sashank
21 | 04.Doctor and Clinical Management | 4.02 | Secure Doctor Patient Communication | Create authentication system for users | Y | 2025-04-27 | 2025-04-28 | 100% | Malavika
22 | 04.Doctor and Clinical Management | 4.02 | Secure Doctor Patient Communication | Write logic to store messages securely | Y | 2025-04-28 | 2025-04-29 | 100% | Malavika
23 | 04.Doctor and Clinical Management | 4.02 | Secure Doctor Patient Communication | Test unauthorized access attempts | Y | 2025-04-29 | 2025-04-30 | 100% | Malavika
24 | 04.Doctor and Clinical Management | 4.03 | Digital Prescriptions | Design form for digital prescription input | Y | 2025-04-30 | 2025-05-01 | 100% | Sashank
25 | 04.Doctor and Clinical Management | 4.03 | Digital Prescriptions | Link prescription to patient profile | Y | 2025-05-01 | 2025-05-02 | 100% | Sashank
26 | 04.Doctor and Clinical Management | 4.03 | Digital Prescriptions | Create downloadable prescription format | Y | 2025-05-02 | 2025-05-03 | 100% | Sashank
27 | 04.Doctor and Clinical Management | 4.03 | Digital Prescriptions | Create download and print options | Y | 2025-05-03 | 2025-05-04 | 100% | Sashank
28 | 04.Doctor and Clinical Management | 4.03 | Digital Prescriptions | Write Test Cases: Patient access/download scenarios | N | 2025-05-04 | 2025-05-05 | 100% | Vedang